## G-Mofa ¦ Activities Breakdown
Output | Sub-Sector | # | Activities | Applicable for TPM Yes/No | # Targeted beneficiaries HH's | # Targeted beneficiaries individuals | Overlappng Activity? (Yes/No) If this activity overlaps with other activities, these can be included in the same sample | What activity | Estimated timeline for the monitoring (Please include an estimation of when the monitoring should take place / if unclear write TBD) |  | surveys requested from TPM (Please specify the number- and try to consider gender segregation while deciding on the numbers) |  |  | FGD Requested from TPM (Please specify the number- and try to consider gender segregation while deciding on the numbers) |  |  | # of KII | # of Observation Visit | Questions / Comments
[9 empty] | Starting From | Ending in | Surveys with Male | Surveys with female | Total Surveys | FGDs with Male | FGDs with Female | Total FGDs | Total KII | Total Observation
Output 1 | SRH | SRH - 1 | Provide Health Services through AMAL Hospital | Yes | N/A | 17305 | No | N/A | 2023-05-23 | 2024-03-24 | 28 | 68 | 376 | 1 | 2 | 3 | 2 | 3 | in A’zaz
|  | SRH - 2 | Provide primary health care services in PHC Center in A'zaz | Yes | N/A | 10084 | No | N/A | 2023-05-23 | 2024-03-24 | 28 | 67 | 95 | 1 | 2 | 3 | 2 | 3
|  | SRH - 3 | Provide transportation between IDP and urban sites and health facilities | No | N/A | 8899 | Yes | SRH-1 , SRH-2 | 2023-06-23 | 2024-03-24 |  |  | 0 |  |  | 0
|  | SRH - 4 | Provide community health awareness raising sessions by Community Health/Outreach Workers | Yes | N/A | 10626 | Yes | SRH-1 , SRH-2 | 2023-05-23 | 2024-03-24
|  | SRH - 5 | Adolescent Mothers Against All Odds (AMAL) Initiative Full Package with advisory group | Yes | N/A | 213 | No | N/A | 2023-05-23 | 2024-03-24 | 0 | 0 | 0 | 2 | 4 | 6 | 3 | 0 | FGD Female 2 YMC - 1 Community members 1- service provider Male : 1 Community members KII: Facilitaior per component
Output 2 | Ambulance and First Aid
|  | AF - 1 | Referrals of patients through ambulance referral system to health facilities - 3 networks | No | N/A | 5040 | Yes | SRH-1 , SRH-2 | 2023-06-23 | 2024-01-24 | 0 | 0 | 0
|  | AF - 2 | Provide first aid to patients by paramedics for 3 ambulance networks | No | N/A | 1000 | No | N/A | 2023-06-23 | 2024-01-24 |  |  | 0
|  | AF - 3 | Train community members on first aid | No | N/A | 150 | No | N/A | 2023-06-23 | 2024-01-24 |  |  | 0
Output 3 | Protection
|  | P-1 | Train non specialised humanitarian workers on GBV core concepts and risk mitigation | Yes | N/A | 50 | No | N/A | 2023-07-23 | 2023-11-24 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | All KIIs are activity particpants
|  | P-2 | Provide GBV case management (CM) and psychosocial support (PSS) for GBV survivors and women and girls at high risk of GBV | No | N/A | 250 | No | N/A | 2023-05-23 | 2024-03-24 | 0 | 0 | 0
|  | P-3 | Provide women, girls and boys PSS and life skills activities in WGSSs and outreach | Yes | N/A | 780 | No | N/A | 2023-05-23 | 2024-03-24 | 28 | 58 | 86 | 3 | 3 | 6 | 4 | 3
|  | P-4 | Provide GBV awareness raising, information sessions and community events | Yes | N/A | 2195 | No | N/A | 2023-05-23 | 2024-03-24 | 46 | 46 | 92 | 0 | 0 | 0 | 0 | 0
Output 4 | Winterization
|  | ER-1 | Winterization vouchers (Commodity voucher) | Yes | 6940 | 34700 | No | N/A | 2023-11-23 | 2024-02-24 | 181 | 182 | 363 | 2 | 2 | 4 | 4 | 0 | Local Authority, Partner focal point, 2- Vendor
|  | ER-2 | NFI and hygiene kits | Yes | 1000 | 5000 | No | N/A | 2023-11-23 | 2024-02-24 | 46 | 46 | 94 | 1 | 1 | 2 | 2 | 0 | Local Authority, Partner focal point (each HH receiving both kits)
Output 5 | Cash For Food
|  | ER-3 | Distribution and redemption of e-voucher (Commodity voucher) | Yes | 4300 | 21500 | No | N/A | 2023-09-23 | 2024-03-24 | 175 | 176 | 351 | 2 | 2 | 4 | 4 | 0 | Local Authority, Partner focal point, 2- Vendor, Only 2 locations
Output 6 | WASH
|  | W-1 | Rehabilitation and operation of water systems with maintenance and extension for existing water networks and water quality treatement | Yes | N/A | 29801 | No | N/A | 2023-04-23 | 2024-03-24 | 95 | 95 | 190 | 2 | 2 | 4 | 4 | 6 | Suggested KII: (1- Local Council (2- Water station worker
|  | W-2 | Water trucking, water quality treatment and provision of all required storage tanks in camps and informal sites | Yes | N/A | 27252 | Yes | W-4 | 2023-04-23 | 2024-03-24 | 189 | 190 | 379 | 4 | 4 | 8 | 6 | 0 | Suggested KII 6 locatons: (1- Camp Management (2- Partner field focal point
|  | W-3 | Sewage network rehabilitation/extend sewage and drainage systems. | Yes | N/A | 23409 | No | N/A | 2023-06-23 | 2024-01-24 | 95 | 95 | 190 | 1 | 1 | 2 | 2 |  | Suggested KII: (1- Local Council (2- Partner field focal point
|  | W-4 | Rehabilitation of latrines and handwashing stations and provide desludging services | Yes | N/A | 11806 | Yes | W-2 | 2023-04-23 | 2024-03-24 | 189 | 190 | 379 | 4 | 4 | 8 | 6 | 0 | Suggested KII 6 locatons: (1- Camp Management (2- Partner field focal point
|  | W-5 | Solid waste management including garbage collection and distribution of garbage bins | Yes | N/A | 48900 | Yes | W-2 , W-4 | 2023-04-23 | 2024-03-24 | 189 | 190 | 379 | 4 | 4 | 8 | 6 | 0 | Suggested KII 6 locatons: (1- Camp Management (2- Partner field focal point
|  | W-6 | Hygiene promotion & Distribution of Soup | Yes | N/A | 27738 | Yes | N/A | 2023-04-23 | 2024-03-24 | 189 | 190 | 379 | 4 | 4 | 8 | 6 | 0 | Suggested KII 6 locatons: (1- Camp Management (2- Partner field focal point
Output 7 | Shelter - Settlement
|  | S-1 | Emergency site improvements in response to floods including levelling and gravelling main and sub roads at IDP sites, leveling and raising shelter bases and establishing rainwater drainage systems to ensure adequate drainage towards catchment basins, improve access for essential services and ensure dignified and safer living conditions in IDP sites in line with NWS Shelter/NFI Cluster guidance | Yes | N/A | 21500 | No | N/A | 2023-08-23 | 2024-01-24 | 0 | 0 | 0 | 2 | 2 | 4 | 2 | 4 | Suggested KII: (1- Camp Management (2- Partner field focal point
| Sector |  | Total # of BNFs | # of Suveys | # of FGD | KII | # Observation | Reports
| SRH |  | 27602 | 471 | 12 | 7 | 6 | 3
| Protection |  | 3025 | 178 | 6 | 10 | 3
| Winterization |  | 39700 | 457 | 6 | 6 | 0
| Cash For Food |  | 21500 | 351 | 4 | 4 | 0
| WASH |  | 84791 | 759 | 14 | 12 | 6
| Shelter - Settlement |  |  | 0 | 4 | 2 | 4
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CEMONC , Gynocology , General SRH , Referal. Reply: also Pediatreic , nutrition Reply: till now the CEmONC will be ended in 31st Nov23 , while from 1st Dec23 till 31st Mar it will be BEmONC
Note on R18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It can be 2 KII
Note on S23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rashed Can we make this at least 6? one per station