## ECHO ¦ Activities Breakdown
Sector | Sub-Sector | Activities | Applicable for TPM Yes/No | # Targeted beneficiaries Households | # Targeted beneficiaries individuals | Overlappng Activity? (Yes/No) If this activity overlaps with other activities, these can be included in the same sample | Estimated timeline for the monitoring (Please include an estimation of when the monitoring should take place / if unclear write TBD) |  | surveys requested from TPM (Please specify the number- and try to consider gender segregation while deciding on the numbers) |  |  | FGD Requested from TPM (Please specify the number- and try to consider gender segregation while deciding on the numbers) |  |  | # of KII | # of Observation Visit | Questions / Comments
[7 empty] | Starting From | Ending in | Surveys with Male | Surveys with female | Total Surveys | FGDs with Male | FGDs with Female | Total FGDs | Total KII | Total Observation
WASH | Provision of sufficient, safe water supplies | Water trucking | Yes | N/A | 129670 | Yes | 2023-04-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 4 | 7 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
|  | Water stations operation | Yes | N/A |  | No | 2023-04-23 | 2023-02-24 | 71 | 71 | 142 | 3 | 3 | 6 | 4 | 0 | Uniqe
|  | Water systems rehabilitation including solar systems and water network | Yes | N/A |  | N/A | 2023-09-23 | 2023-02-24 | N/A | N/A | 0 |  |  | 0 | 4 | 2 | Those activites are packege in the same locations , Same BNFs same Sample
| Provision of solid waste management services. | Solid waste collection - SWM | Yes | N/A | 2994 | Yes | 2023-04-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 3 | 6 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
| Sanitation | desludging services | Yes | N/A | 6000 | Yes | 2023-04-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 3 | 6 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
|  | sanitation and drainage systems | Yes | N/A |  | No | 2023-09-23 | 2023-02-24 |  |  | 0 | 1 | 1 | 2 | 2 | 0 | Uniqe
|  | Install and maintain latrines/ hand washing stations. | Yes | N/A |  | Yes | 2023-09-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 3 | 6 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
| safe hygiene behaviors | Hygiene promotion sessions | Yes | N/A | 40000 | Yes | 2023-04-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 3 | 6 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
|  | Soap kits distribution | Yes | N/A |  | Yes | 2023-04-23 | 2023-02-24 | 192 | 192 | 384 | 3 | 3 | 6 | 0 | 0 | Those activites are packege in the same locations , Same BNFs same Sample
Protection | GBV and protection risks | GBV case management services for GBV survivors | No | NA | 510 | No | 2023-08-01 | 2024-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Psychosocial support (PSS) through individual and group counselling | Yes | NA | 610 | No | 2023-08-01 | 2024-02-15 | 81 | 122 | 149 | 2 | 2 | 4 | 0 | 4 | only group session could be monitored. The target for it is 425
|  | Facilitation of referrals for individuals at risk of GBV and protection violations through mobile outreach and protection help desks | No | NA | 275 | No | 2023-08-01 | 2024-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Protection information provision to women, girls, boys and men | Yes | NA | 3600 | No | 2023-08-01 | 2024-02-15 |  |  | 94 | 0 | 0 | 0 | 0 | 4
|  | Provision of structured GBV awareness raising,life skills and skills building sessions | Yes | NA | 6500 | No | 2023-08-01 | 2024-02-15 | 83 | 280 | 303 | 10 | 10 | 10 | 6 | 6 | we have 6 sub activities under this , TP- Male and Female ,GBV - M & F ,AMAL - M & F EMB - M ,life skills M&F skills building sessions - F so can we create one common FGD tool for the 4 mentioned sub activiites
|  | Women Led- Action Planning and Safety Audits | Yes | NA | 100 | No | 2023-08-01 | 2024-02-15 | 0 | 0 | 0 | 0 | 2 | 2 | 6 | 0 | 4 women led network , 2 community committee
Food Security & Livelihoods | Income generation opportunities | business grant to start new/ re-establishing existing businesses | Yes | 400 | 2000 | No | 2023-08-01 | 2024-02-28 | 15 | 25 | 40 | 2 | 3 | 5 | 0 | 20 | 20 BNFs starting a new business or re-establishing exsisting business
Earthquake response | MPCA | MPCA Distribution | Yes | 11400 | 57000 | No | 2023-08-01 | 2023-10-01 | 191 | 191 | 382 | 3 | 3 | 6 | 6 | 12 | Partner staff - 3 KII Local Athourties - 3 KII
Shelter and settlements | Winterization | Distribution of winterization cash assistance | Yes | 8200 | 41000 | No | 2023-10-01 | 2023-11-30 | 191 | 191 | 382 | 1 | 1 | 2 | 2 | 15 | Violet Only we might have another partner
| Sector | Total # of BNFs | # of Suveys | # of FGD | KII | # Observation
| WASH | 129670 | 526 | 15 | 10 | 2
| Protection | 11595 | 546 | 16 | 12 | 14
| LER | 2000 | 40 | 5 | 0 | 20
| ER | 98000 | 764 | 8 | 8 | 27
|  |  | 1876 | 44 | 30 | 63